## Risk Management Plan
| Date | 2026-01-01
| Project Mngr |  | Name | abd mahmoud
None
Priority | PROJECT RISK MANAGEMENT PLAN | [25 empty] | WBS 100 Project Management
| Identification | [5 empty] | Qualitative Analysis | [9 empty] | Quantitative Analysis |  |  |  | Response Strategy |  |  | Monitoring and Control |  |  | WBS 150 Develop Project Initiation Document (PID)
| Status | ID # | Date Identified Project Phase | Functional Assignment | Threat/Opportunity Event | Risk Trigger | Type | Probability | Impact | Risk Matrix | [7 empty] | Probability (%) | Impact ($ or days) | Effect ($ or days) | Strategy | Response Actions including advantages and disadvantages | Affected WBS Tasks | Responsibilty (Task Manager) | Status Interval or Milestone Check | Date, Status and Review Comments | WBS 160 Perform Preliminary Engineering Studies and Prepare Draft Project Report
| Active |  | PID |  |  |  | Scope | Very High | Very High | [8 empty] | 0.9 |  |  | Avoidance | [5 empty] | WBS 165 Perform Environmental Studies and Prepare Draft Environmental Document (DED)
| Dormant |  | PA&ED |  |  |  | Schedule | High | High | [8 empty] | 0.7 |  |  | Transference | [5 empty] | WBS 175 Circulate Draft Environmental Document and Select Preferred Project Alternative
| Retired |  | PS&E |  |  |  | Cost | Moderate | Moderate | [8 empty] | 0.5 |  |  | Mitigation | [5 empty] | WBS 180 Prepare and Approve Project Report and Final Environmental Document
|  |  | Construction |  |  |  | Quality | Low | Low | [8 empty] | 0.3 |  |  | Acceptance | [5 empty] | WBS 185 Prepare Base Maps and Plan Sheets
[8 empty] | Very Low | Very Low | [8 empty] | 0.1 |  |  | N/A | [5 empty] | WBS 190 Prepare Structure Site Plans
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | [6 empty] | (12) |  | (13) | (14) =(13)x(12) | (15) | (16) | (17) | (18) | (19) | (20) | WBS 195 Right of Way Property Management and Excess Land
| Active | OA-R001 | 2025-11-01 Planning | Order Automation | Non-order email matches subject keywords and gets processed as an order. | Increase in Processed emails with empty/odd item extraction or customer complaints. | Quality | Moderate | Moderate | Probability | VH | [5 empty] | #REF! | 40% | 2 | 0.8 | Mitigation | Tighten keyword list; optionally add sender allow/deny list; require minimum item-structure match before treating as an order. If extraction confidence is low, route to NeedInfo instead of Processed. | Email intake & identification; Order extraction; Outcome routing | Mailbox/Admin + Developer | Weekly during build; monthly after go-live | 2025-11-01 - Identified during Planning. Next review: 2025-11-08. | WBS 230 Prepare Draft PS&E
[11 empty] | H | [5 empty] | #REF!
[11 empty] | M |  |  | X |  |  | #REF!
[11 empty] | L | [5 empty] | #REF! | [9 empty] | WBS 235 Mitigate Environmental Impacts and Clean-up Hazardous Waste
[11 empty] | VL | [5 empty] | #REF! | [9 empty] | WBS 240 Prepare Draft Structures PS&E
[12 empty] | VL | L | M | H | VH | [10 empty] | WBS 245 Post Right of Way Certification Work
[12 empty] | Impact | [14 empty] | WBS 250 Prepare Final Structures PS&E Package
WBS 255 Circulate, Review, and Prepare Final District PS&E Package
| Active | OA-R002 | 2025-11-05 Planning | Order Automation | Real orders are missed due to incomplete keyword rules (false negatives). | Ops reports missing expected orders; order volume mismatch vs manual checks. | Scope | Moderate | High | Probability | VH | [5 empty] | #REF! | 40% | 5 | 2 | Mitigation | Expand keywords; add optional body phrase detection; maintain a periodic inbox review process until detection stabilizes. | Email intake & identification; Monitoring & controls | Ops Owner + Mailbox/Admin | Weekly during build; monthly after go-live | 2025-11-05 - Identified during Planning. Next review: 2025-11-12. | WBS 230 Prepare Draft PS&E
[11 empty] | H | [5 empty] | #REF!
[11 empty] | M |  |  |  | X |  | #REF!
[11 empty] | L | [5 empty] | #REF! | [9 empty] | WBS 235 Mitigate Environmental Impacts and Clean-up Hazardous Waste
[11 empty] | VL | [5 empty] | #REF! | [9 empty] | WBS 240 Prepare Draft Structures PS&E
[12 empty] | VL | L | M | H | VH | [10 empty] | WBS 245 Post Right of Way Certification Work
[12 empty] | Impact | [14 empty] | WBS 250 Prepare Final Structures PS&E Package
WBS 255 Circulate, Review, and Prepare Final District PS&E Package
| Active | OA-R003 | 2025-11-09 Planning | Order Automation | Email body format differs from supported patterns; extraction fails and NeedInfo volume spikes. | NeedInfo rate increases; repeated parse failures from same sender. | Quality | High | Moderate | Probability | VH | [5 empty] | 0 | 60% | 2 | 1.2 | Mitigation | Add/extend parsing patterns (comma/pipe/labeled); build unit tests for each format; add normalization and validation for product/qty/price fields. | Order extraction; Reliability & QA | Developer + QA | Weekly during build; monthly after go-live | 2025-11-09 - Identified during Planning. Next review: 2025-11-16. | WBS 230 Prepare Draft PS&E
[11 empty] | H |  |  | X |  |  | 0
[11 empty] | M | [5 empty] | 0
[11 empty] | L | [5 empty] | 0 | [9 empty] | WBS 235 Mitigate Environmental Impacts and Clean-up Hazardous Waste
[11 empty] | VL | [5 empty] | 0 | [9 empty] | WBS 240 Prepare Draft Structures PS&E
[12 empty] | VL | L | M | H | VH | [10 empty] | WBS 245 Post Right of Way Certification Work
[12 empty] | Impact | [14 empty] | WBS 250 Prepare Final Structures PS&E Package
WBS 255 Circulate, Review, and Prepare Final District PS&E Package
| Active | OA-R004 | 2025-11-13 Planning | Order Automation | Incorrect parsing (wrong qty/price) silently produces wrong totals/ETA and wrong restock updates. | Totals not matching line items; unusual quantities/prices; customer disputes. | Quality | Low | Very High | Probability | VH | [5 empty] | 0 | 20% | 10 | 2 | Avoidance / Mitigation | Strict validation rules (qty>0, numeric parsing, currency handling); cross-check line total=qty×unit price; sanity bounds; if validation fails, route to NeedInfo (no downstream updates). | Order extraction; Calculations & business rules; Restock update | Developer | Weekly during build; monthly after go-live | 2025-11-13 - Identified during Planning. Next review: 2025-11-20. | WBS 230 Prepare Draft PS&E
[11 empty] | H | [5 empty] | 0
[11 empty] | M | [5 empty] | 0
[11 empty] | L |  |  |  |  | X | 0 | [9 empty] | WBS 235 Mitigate Environmental Impacts and Clean-up Hazardous Waste
[11 empty] | VL | [5 empty] | 0 | [9 empty] | WBS 240 Prepare Draft Structures PS&E
[12 empty] | VL | L | M | H | VH | [10 empty] | WBS 245 Post Right of Way Certification Work
[12 empty] | Impact | [14 empty] | WBS 250 Prepare Final Structures PS&E Package
WBS 255 Circulate, Review, and Prepare Final District PS&E Package
| Active | OA-R005 | 2025-11-17 Design | Order Automation | Duplicate processing of the same email causes double increments in the restock spreadsheet. | Same sender/subject processed multiple times; repeated internal IDs; spreadsheet jump anomalies. | Cost | Moderate | Very High | Probability | VH | [5 empty] | 0 | 40% | 10 | 4 | Avoidance / Mitigation | Persist processed message IDs; make restock update idempotent keyed by message ID; detect duplicates and skip downstream actions (log + route to Failed/NeedInfo). | Email processing loop; Restock update; Logging | Developer + Ops Owner | Weekly during build; monthly after go-live | 2025-11-17 - Identified during Design. Next review: 2025-11-24. | WBS 230 Prepare Draft PS&E
[11 empty] | H | [5 empty] | 0
[11 empty] | M |  |  |  |  | X | 0
[11 empty] | L | [5 empty] | 0 | [9 empty] | WBS 235 Mitigate Environmental Impacts and Clean-up Hazardous Waste
[11 empty] | VL | [5 empty] | 0 | [9 empty] | WBS 240 Prepare Draft Structures PS&E
[12 empty] | VL | L | M | H | VH | [10 empty] | WBS 245 Post Right of Way Certification Work
[12 empty] | Impact | [14 empty] | WBS 250 Prepare Final Structures PS&E Package
WBS 255 Circulate, Review, and Prepare Final District PS&E Package
| Active | OA-R006 | 2025-11-21 Design | Order Automation | Attachments fail to save or overwrite due to filename collisions. | Missing attachments on disk; identical filenames from different emails. | Quality | Moderate | High | Probability | VH | [5 empty] | 0 | 40% | 5 | 2 | Mitigation | Save to configured folder with one subfolder per email; include unique ID in folder/file names; check disk space and retry transient IO. | Attachments handling; Logging & audit trail | Developer | Weekly during build; monthly after go-live | 2025-11-21 - Identified during Design. Next review: 2025-11-28. | WBS 230 Prepare Draft PS&E
[11 empty] | H | [5 empty] | 0
[11 empty] | M |  |  |  | X |  | 0
[11 empty] | L | [5 empty] | 0 | [9 empty] | WBS 235 Mitigate Environmental Impacts and Clean-up Hazardous Waste
[11 empty] | VL | [5 empty] | 0 | [9 empty] | WBS 240 Prepare Draft Structures PS&E
[12 empty] | VL | L | M | H | VH | [10 empty] | WBS 245 Post Right of Way Certification Work
[12 empty] | Impact | [14 empty] | WBS 250 Prepare Final Structures PS&E Package
WBS 255 Circulate, Review, and Prepare Final District PS&E Package
| Active | OA-R007 | 2025-11-25 Design | Order Automation | Restock spreadsheet is locked, corrupted, or its schema changes, causing update failures. | Write errors; missing columns; file lock conflicts. | Cost | Moderate | Very High | Probability | VH | [5 empty] | 0 | 40% | 10 | 4 | Mitigation | Validate schema before write; create timestamped backup; handle file locks with retry/backoff; on failure route to Failed and alert Ops (no partial writes). | Restock tracker update; Reliability & error handling | Developer + Ops Owner | Weekly during build; monthly after go-live | 2025-11-25 - Identified during Design. Next review: 2025-12-02. | WBS 230 Prepare Draft PS&E
[11 empty] | H | [5 empty] | 0
[11 empty] | M |  |  |  |  | X | 0
[11 empty] | L | [5 empty] | 0 | [9 empty] | WBS 235 Mitigate Environmental Impacts and Clean-up Hazardous Waste
[11 empty] | VL | [5 empty] | 0 | [9 empty] | WBS 240 Prepare Draft Structures PS&E
[12 empty] | VL | L | M | H | VH | [10 empty] | WBS 245 Post Right of Way Certification Work
[12 empty] | Impact | [14 empty] | WBS 250 Prepare Final Structures PS&E Package
WBS 255 Circulate, Review, and Prepare Final District PS&E Package
| Active | OA-R008 | 2025-12-03 Build | Order Automation | Misconfigured delivery-days rule generates incorrect ETA in follow-up messages. | ETAs inconsistent with policy; unusually far/near dates. | Schedule | Moderate | Moderate | Probability | VH | [5 empty] | 0 | 40% | 2 | 0.8 | Mitigation | Validate settings (bounds checks); show preview in Settings UI; keep default values sane; block run on invalid configuration.Validate settings (bounds checks); show preview in Settings UI; keep default values sane; block run on invalid configuration. | Settings UI; Calculations & business rules | Project Owner + Developer | Weekly during build; monthly after go-live | 2025-12-03 - Identified during Build. Next review: 2025-12-10. | WBS 230 Prepare Draft PS&E
[11 empty] | H | [5 empty] | 0
[11 empty] | M |  |  | X |  |  | 0
[11 empty] | L | [5 empty] | 0 | [9 empty] | WBS 235 Mitigate Environmental Impacts and Clean-up Hazardous Waste
[11 empty] | VL | [5 empty] | 0 | [9 empty] | WBS 240 Prepare Draft Structures PS&E
[12 empty] | VL | L | M | H | VH | [10 empty] | WBS 245 Post Right of Way Certification Work
[12 empty] | Impact | [14 empty] | WBS 250 Prepare Final Structures PS&E Package
WBS 255 Circulate, Review, and Prepare Final District PS&E Package
| Active | OA-R009 | 2025-12-07 Build | Order Automation | Mailbox foldering fails (missing folders/permissions) leaving status unclear and inbox cluttered. | Emails remain in inbox; move operation errors. | Scope | Low | Moderate | Probability | VH | [5 empty] | #REF! | 20% | 2 | 0.4 | Mitigation | Verify/create outcome folders during initialization; on move failure still write log entry and surface manual action needed. | Setup & initialization; Outcome routing; Logging | Mailbox/Admin | Weekly during build; monthly after go-live | 2025-12-07 - Identified during Build. Next review: 2025-12-14. | WBS 230 Prepare Draft PS&E
[11 empty] | H | [5 empty] | #REF!
[11 empty] | M | [5 empty] | #REF!
[11 empty] | L |  |  | X |  |  | #REF! | [9 empty] | WBS 235 Mitigate Environmental Impacts and Clean-up Hazardous Waste
[11 empty] | VL | [5 empty] | #REF! | [9 empty] | WBS 240 Prepare Draft Structures PS&E
[12 empty] | VL | L | M | H | VH | [10 empty] | WBS 245 Post Right of Way Certification Work
[12 empty] | Impact | [14 empty] | WBS 250 Prepare Final Structures PS&E Package
WBS 255 Circulate, Review, and Prepare Final District PS&E Package
| Active | OA-R010 | 2025-12-11 Build | Order Automation | Log record is missing or does not reflect final status after downstream actions (audit gap). | Mismatch between folder status and log; missing attachment paths in log. | Quality | Low | Very High | Probability | VH | [5 empty] | 0 | 20% | 10 | 2 | Avoidance / Mitigation | Log only after all actions complete; enforce required fields; retry log writes; if logging fails, treat as Failed and alert for reconciliation. | Logging & audit trail; Reliability & error handling | Developer | Weekly during build; monthly after go-live | 2025-12-11 - Identified during Build. Next review: 2025-12-18. | WBS 230 Prepare Draft PS&E
[11 empty] | H | [5 empty] | 0
[11 empty] | M | [5 empty] | 0
[11 empty] | L |  |  |  |  | X | 0 | [9 empty] | WBS 235 Mitigate Environmental Impacts and Clean-up Hazardous Waste
[11 empty] | VL | [5 empty] | 0 | [9 empty] | WBS 240 Prepare Draft Structures PS&E
[12 empty] | VL | L | M | H | VH | [10 empty] | WBS 245 Post Right of Way Certification Work
[12 empty] | Impact | [14 empty] | WBS 250 Prepare Final Structures PS&E Package
WBS 255 Circulate, Review, and Prepare Final District PS&E Package
| Active | OA-R011 | 2025-12-15 Build | Order Automation | Security/privacy issue: attachments or logs stored in an insecure location or with overly broad permissions. | Unauthorized access report; storage path not approved. | Quality | Low | Very High | Probability | VH | [5 empty] | 0 | 20% | 10 | 2 | Avoidance / Mitigation | Use least-privilege permissions; store only in configured approved folder; minimize sensitive data in logs; rotate credentials and audit access after any incident. | Settings; Attachments handling; Logging | Project Owner + Mailbox/Admin | Weekly during build; monthly after go-live | 2025-12-15 - Identified during Build. Next review: 2025-12-22. | WBS 230 Prepare Draft PS&E
[11 empty] | H | [5 empty] | 0
[11 empty] | M | [5 empty] | 0
[11 empty] | L |  |  |  |  | X | 0 | [9 empty] | WBS 235 Mitigate Environmental Impacts and Clean-up Hazardous Waste
[11 empty] | VL | [5 empty] | 0 | [9 empty] | WBS 240 Prepare Draft Structures PS&E
[12 empty] | VL | L | M | H | VH | [10 empty] | WBS 245 Post Right of Way Certification Work
[12 empty] | Impact | [14 empty] | WBS 250 Prepare Final Structures PS&E Package
WBS 255 Circulate, Review, and Prepare Final District PS&E Package