## Risk Plan
Project |  |  | Email Order Processing Automation RPA
Start |  |  | 2025-12-01
End |  |  | 2025-12-24
Project Manager |  |  | Sakka Mohamad-Mario
Team |  |  | Sakka Mohamad-Mario, Mirghani Abdelrahman, Zafar Azzam, Al-Khalidy Essam
PROJECT RISK MANAGEMENT PLAN
|  |  | Identification | [5 empty] | Qualitative Analysis |  |  | Quantitative Analysis |  |  |  | Response Strategy |  | Monitoring and Control
Priority | Status | ID # | Date Identified | Project Phase | Functional Assignment | Threat/Opportunity Event | Risk Trigger | Type | Probability (β) | Impact (i) | Risk Matrix | Probability (λ) | Impact ($ or days) | Effect ($ or days) | Strategy | Response Actions including advantages and disadvantages | Affected WBS Tasks | Responsibility (Task Manager) | Status Interval or Milestone Check | Date, Status and Review Comments
Medium | Active | OA-R001 | 2025-12-01 | Planning | Order Automation | Non-order email matches subject keywords and gets processed as an order. | Increase in Processed emails with empty/odd item extraction or customer complaints. | Quality | Possible | Moderate |  | 40% | 2 | 0.8 | Mitigate | Tighten keyword list; optionally add sender allow/deny list; require minimum item-structure match before treating as an order. If extraction confidence is low, route to NeedInfo instead of Processed. | Email intake & identification; Order extraction; Outcome routing | Zafar Azzam | Weekly during build; monthly after go-live | 2025-12-01 - Identified during Planning. Next review: 2025-12-08.
Medium | Active | OA-R002 | 2025-12-05 | Planning | Order Automation | Real orders are missed due to incomplete keyword rules (false negatives). | Ops reports missing expected orders; order volume mismatch vs manual checks. | Scope | Possible | Moderate |  | 40% | 5 | 2 | Mitigate | Expand keywords; add optional body phrase detection; maintain a periodic inbox review process until detection stabilizes. | Email intake & identification; Monitoring & controls | Zafar Azzam | Weekly during build; monthly after go-live | 2025-12-05 - Identified during Planning. Next review: 2025-12-12.
Medium | Active | OA-R003 | 2025-12-09 | Planning | Order Automation | Email body format differs from supported patterns; extraction fails and NeedInfo volume spikes. | NeedInfo rate increases; repeated parse failures from same sender. | Quality | Possible | Moderate |  | 60% | 2 | 1.2 | Mitigate | Add/extend parsing patterns (comma/pipe/labeled); build unit tests for each format; add normalization and validation for product/qty/price fields. | Order extraction; Reliability & QA | Al-Khalidy Essam | Weekly during build; monthly after go-live | 2025-12-09 - Identified during Planning. Next review: 2025-12-16.
Medium | Active | OA-R004 | 2025-12-13 | Planning | Order Automation | Incorrect parsing (wrong qty/price) silently produces wrong totals/ETA and wrong restock updates. | Totals not matching line items; unusual quantities/prices; customer disputes. | Quality | Possible | Major |  | 20% | 10 | 2 | Mitigate | Strict validation rules (qty>0, numeric parsing, currency handling); cross-check line total=qty×unit price; sanity bounds; if validation fails, route to NeedInfo (no downstream updates). | Order extraction; Calculations & business rules; Restock update | Al-Khalidy Essam | Weekly during build; monthly after go-live | 2025-12-13 - Identified during Planning. Next review: 2025-12-20.
High | Active | OA-R005 | 2025-12-17 | Design | Order Automation | Duplicate processing of the same email causes double increments in the restock spreadsheet. | Same sender/subject processed multiple times; repeated internal IDs; spreadsheet jump anomalies. | Cost | Possible | Major |  | 40% | 10 | 4 | Mitigate | Persist processed message IDs; make restock update idempotent keyed by message ID; detect duplicates and skip downstream actions (log + route to Failed/NeedInfo). | Email processing loop; Restock update; Logging | Sakka Mohamad-Mario | Weekly during build; monthly after go-live | 2025-12-17 - Identified during Design. Next review: 2025-12-24.
Medium | Active | OA-R006 | 2025-12-21 | Design | Order Automation | Attachments fail to save or overwrite due to filename collisions. | Missing attachments on disk; identical filenames from different emails. | Quality | Likely | Critical |  | 40% | 5 | 2 | Mitigate | Save to configured folder with one subfolder per email; include unique ID in folder/file names; check disk space and retry transient IO. | Attachments handling; Logging & audit trail | Al-Khalidy Essam | Weekly during build; monthly after go-live | 2025-12-21 - Identified during Design. Next review: 2025-12-24.
High | Active | OA-R007 | 2025-12-23 | Design | Order Automation | Restock spreadsheet is locked, corrupted, or its schema changes, causing update failures. | Write errors; missing columns; file lock conflicts. | Cost | Unlikely | Critical |  | 40% | 10 | 4 | Mitigate | Validate schema before write; create timestamped backup; handle file locks with retry/backoff; on failure route to Failed and alert Ops (no partial writes). | Restock tracker update; Reliability & error handling | Sakka Mohamad-Mario | Weekly during build; monthly after go-live | 2025-12-23 - Identified during Design. Next review: 2025-12-24.
Medium | Active | OA-R008 | 2025-12-03 | Build | Order Automation | Misconfigured delivery-days rule generates incorrect ETA in follow-up messages. | ETAs inconsistent with policy; unusually far/near dates. | Schedule | Unlikely | Critical |  | 40% | 2 | 0.8 | Mitigate | Validate settings (bounds checks); show preview in Settings UI; keep default values sane; block run on invalid configuration.Validate settings (bounds checks); show preview in Settings UI; keep default values sane; block run on invalid configuration. | Settings UI; Calculations & business rules | Mirghani Abdelrahman | Weekly during build; monthly after go-live | 2025-12-03 - Identified during Build. Next review: 2025-12-10.
Medium | Active | OA-R009 | 2025-12-07 | Build | Order Automation | Mailbox foldering fails (missing folders/permissions) leaving status unclear and inbox cluttered. | Emails remain in inbox; move operation errors. | Scope | Unlikely | Critical |  | 20% | 2 | 0.4 | Mitigate | Verify/create outcome folders during initialization; on move failure still write log entry and surface manual action needed. | Setup & initialization; Outcome routing; Logging | Mirghani Abdelrahman | Weekly during build; monthly after go-live | 2025-12-07 - Identified during Build. Next review: 2025-12-14.
Medium | Active | OA-R010 | 2025-12-11 | Build | Order Automation | Log record is missing or does not reflect final status after downstream actions (audit gap). | Mismatch between folder status and log; missing attachment paths in log. | Quality | Rare | Critical |  | 20% | 10 | 2 | Mitigate | Log only after all actions complete; enforce required fields; retry log writes; if logging fails, treat as Failed and alert for reconciliation. | Logging & audit trail; Reliability & error handling | Al-Khalidy Essam | Weekly during build; monthly after go-live | 2025-12-11 - Identified during Build. Next review: 2025-12-18.